## List
Activ8 Project
WBS | Task | Predec. | Start Date | Finish Date
1 | Activ8 Project
1.01 | Architecture definition
1.01.01 | First version |  | 2009-07-27 |  | * Need to place dates even if already passed….
1.01.01.01 | Service Defintion
1.01.01.01a | Researcher services
1.01.01.01b | Transversal services
1.01.01.01c | Patient services
1.01.01.01d | Service definition completed and validated (milestone)
1.01.01.02a | Incorporation of example of Researcher Case
1.01.01.02b | Incorporation of Transversal Services Case
1.01.01.02c | Incorporation of Patient Services Case
1.01.01.03 | Service Plaform defined and validated
1.01.01.04 | Software architecture
1.01.01.05 | Physical architecture
1.01.01.06 | Archtectual document complete (milestone)
1.01.01.07 | Mashup Demo
1.01.02.07 | Website Demo complete utilizing patient-clinician-research link example
1.01.03.01 | Scientific review
1.01.03.02 | Technological review
1.01.02 | Second version | 1.01.01
1.01.02.01 | Design of external interfaces
1.01.02.02 | Patient services
1.01.02.03 | Clinical services
1.01.02.04 | Monitoring Demo
1.01.02.05 | Data model
1.01.02.06 | Virtual World Demo
1.01.02.07 | Incorporation of example of Researcher Case 2
1.01.02.08 | Incorporation of example of Clinical Case
1.01.02.09 | Web Demo
1.01.03 | Review | 1.01.02
1.01.03.01 | Scientific review
1.01.03.02 | Technological review
1.01.03.03 | Services review
1.01.03.04 | Overall review
1.02 | Proposal | 1.01
1.02.01 | First version
1.02.01.01 | Abstract, Introduction and Importance
1.02.01.02 | Scientific background and implementation
1.02.01.03 | Technical background and implementation
1.02.01.04 | Cost and budgets
1.02.01.05 | Work packages
1.02.02 | Second version
1.02.02.01 | First version review
1.02.02.02 | Scientific and technical changes of definition
1.02.02.03 | Project implementation changes of definition
1.02.03 | Reviews
1.02.03.01 | Scientific and technical quality
1.02.03.02 | Implementation of the project
1.02.03.03 | Impact of the project
1.03 | Deployment | 1.04
1.03.01 | First version
1.03.01.01 | Web navigation
1.03.01.02 | Monitoring and Web communication
1.03.01.03 | Virtual World and Web communication
1.03.01.04 | Services skleton

## To Dos
Things to be completed in July
Contact FEDER - get links
Contact INB - working from INB office
Contact Carlos III - establish relationship
Things to be completed in August